## Sheet1
AQC Animal Health App — POC Backlog (Waterfall)
One row per work item. Filter by Phase, Module, Layer or Scope. Effort is in person-days (blue = editable estimate).
ID | Phase | Module | Layer | Title | Description / user story | Acceptance criteria | Figma screen | Priority | Effort (days) | Depends on | Scope | Status | Owner | Notes
DES-007 | 2. Design | M6 AI Routing & Extraction | AI | AI design: prompts, schemas and thresholds | Design prompts and JSON output schemas for animal matching, sign extraction, routing and 30-day summaries. Set confidence thresholds and the fallback behaviour. | • Prompt v1 and JSON schemas documented • Threshold and review-queue rules agreed with AVS |  | Must | 4 | REQ-004, REQ-005 | POC core | Not started
BE-001 | 3. Build | Platform / Cross-cutting | Backend | API service skeleton (NestJS) | Create the NestJS app with module structure, config from Key Vault, validation pipes, global error format, health endpoints and Swagger from the OpenAPI spec. | • /health returns DB and queue status • Errors follow one JSON error format |  | Must | 3 | INF-001 | POC core | Not started
BE-002 | 3. Build | Platform / Cross-cutting | Backend | Database schema and migrations | Implement all tables with Prisma migrations: users, kennels, animals, stays, exams, inspections, observations, media, medication, cases, AI results, summaries, notifications, audit. | • Migrations run cleanly on an empty DB • Foreign keys and indexes match the ERD |  | Must | 4 | BE-001, DES-005 | POC core | Not started
BE-003 | 3. Build | M11 Administration | Backend | Seed and reference data | Seed kennels/rooms, species, checklist templates, symptom taxonomy, AQC glossary and demo users for each role. | • One command seeds Dev/UAT • Demo data includes 20 animals across kennels |  | Must | 1 | BE-002 | POC core | Not started
BE-004 | 3. Build | Platform / Cross-cutting | Backend | Authentication (two identity providers) | Validate JWTs from the officer IdP and the contractor IdP. Create or update the user record on first login and map IdP groups to app roles. | • Tokens from both IdPs accepted; others rejected • First login creates the user with the correct role |  | Must | 3 | BE-001, INF-007 | POC core | Not started
BE-005 | 3. Build | Platform / Cross-cutting | Backend | Authorisation: RBAC and data scoping | Guards that enforce the permission matrix on every endpoint. Contractors only see animals in kennels assigned to them. | • Automated tests cover every role x endpoint rule • Out-of-scope access returns 403 and is audited |  | Must | 3 | BE-004, REQ-006 | POC core | Not started
BE-006 | 3. Build | M10 Audit & Traceability | Backend | Audit service | Append-only audit events written for every create/update/status change, AI decision and login. Each event stores user, time, action, entity, before/after and a hash of the previous event. | • No API path can update or delete audit rows • Hash chain verification job passes |  | Must | 4 | BE-002 | POC core | Not started
BE-007 | 3. Build | M11 Administration | Backend | User and role administration API | List, create, disable users; assign roles and kennel scopes; view last login. | • Disabling a user blocks API access immediately • All changes audited |  | Must | 2 | BE-005 | POC core | Not started
BE-008 | 3. Build | M11 Administration | Backend | Master data API | CRUD for kennels/rooms, species, inspection checklist templates, symptom taxonomy, AQC glossary and notification rules. | • Changes to checklist templates apply to new inspections only • Glossary changes are picked up by the AI worker |  | Must | 3 | BE-005 | POC core | Not started
BE-009 | 3. Build | M1 Arrival & Onboarding | Backend | Animal and stay API | Create a new arrival (pet name, kennel/room, species, origin, microchip, sex, DOB, release date), update the profile, list active animals, search by kennel code/name/microchip, and release at end of stay. | • Microchip number unique across active stays • Released animals drop out of active monitoring | 02, 08 | Must | 3 | BE-005 | POC core | Not started
BE-010 | 3. Build | M1 Arrival & Onboarding | Backend | Arrival exam API | Record the arrival baseline exam: examining vet, weight, mentation, physical exam by body system with normal/abnormal and notes. Completing it starts active monitoring. | • Animal status moves to Active monitoring on completion • Abnormal findings create observations for AI routing | 03 | Must | 2 | BE-009 | POC core | Not started
BE-011 | 3. Build | M3 Daily Health Inspection | Backend | Daily inspection API | AM/PM inspection per animal: mentation, skin/coat, eyes, nose, ears, mouth, hydration, cardiorespiratory, food, stool, urine, other findings. Work out checks due per session. | • Only one AM and one PM inspection per animal per day (edits audited) • Any abnormal item or free text publishes an event for AI routing | 04 | Must | 4 | BE-009, BE-016 | POC core | Not started
BE-012 | 3. Build | M4 Ad-hoc Health Observation | Backend | Ad-hoc observation API | Create an observation with text, animal (optional if AI should match) and media references. Return an observation ID to track AI status. | • Observation saved even if AI is unavailable • Status endpoint shows AI processing state | 05 | Must | 2 | BE-009, BE-016 | POC core | Not started
BE-013 | 3. Build | M4 Ad-hoc Health Observation | Backend | Media API (SAS upload and secure read) | Issue short-lived write-only SAS URLs, confirm upload completion, attach media to observations/inspections/cases, and issue short-lived read URLs. | • SAS valid 10 minutes, one blob, write only • Images up to 10 MB and videos up to 100 MB accepted | 05 | Must | 3 | BE-001, INF-002 | POC core | Not started
BE-014 | 3. Build | M4 Ad-hoc Health Observation | Backend | Media worker | Generate image thumbnails and video poster frames, transcode video to a standard MP4, and block files flagged by malware scanning. | • Thumbnails available within 30 seconds • Flagged files are quarantined and never served | 05 | Should | 4 | BE-013 | POC core | Not started
BE-015 | 3. Build | M5 Medication Administration | Backend | Medication API | Manage medication/supplement schedules (item, dose, frequency, start/end) per animal and record administrations with time and officer. Provide a due list. | • Administration auto-captures time and user • Due list shows missed doses | 07 | Must | 3 | BE-009 | POC core | Not started
BE-016 | 3. Build | Platform / Cross-cutting | Backend | Event publishing (outbox pattern) | Write domain events (observation created, inspection abnormal, case changed) to an outbox table and relay them to Service Bus. | • No event lost if Service Bus is down • Events are idempotent by ID |  | Must | 2 | BE-002, INF-002 | POC core | Not started
BE-017 | 3. Build | M8 Health Case Management | Backend | Case API | Create, view, list and filter cases; assign; add follow-up actions, notes and evidence; change status within the allowed transitions; close with a reason. | • Only officers can close • Invalid transitions return 409 | 09 | Must | 4 | BE-005 | POC core | Not started
BE-018 | 3. Build | M8 Health Case Management | Backend | Case rules engine | Apply a confirmed AI routing decision: add to timeline only, update an open case, create a case, or reopen a closed case (same/related signs within the agreed window). Keep all earlier data points linked. | • Reopen keeps previous observations and history • Unit tests cover every rule in REQ-005 | 06, 09 | Must | 4 | BE-017, REQ-005 | POC core | Not started
BE-019 | 3. Build | M6 AI Routing & Extraction | Backend | Review queue API | List observations the AI could not match or scored below threshold. Let an officer pick the animal and case action manually. | • Items leave the queue once triaged • Officer decision recorded against the AI result |  | Must | 2 | BE-018 | POC core | Not started
BE-020 | 3. Build | M2 Animal Profile & Health Record | Backend | Animal health record and timeline API | Return one chronological feed per stay: arrival exam, AM/PM inspections, medication administrations, observations, case events, with media thumbnails. | • Timeline paginates and filters by type/date • Loads within 1 second for a 30-day stay | 08 | Must | 2 | BE-010, BE-011, BE-012, BE-015 | POC core | Not started
BE-021 | 3. Build | M9 Operations Dashboard | Backend | Dashboard API | Today's monitoring counts (active animals, checks due, open cases), the unwell-animal list (animal, status, AI summary, next action) and filters: open, needs review, last 7 days, assigned to me. | • Counts match underlying records • Response under 1 second at 300 active animals | 01, 09 | Must | 3 | BE-017, BE-011 | POC core | Not started
BE-022 | 3. Build | M12 Notifications | Backend | Notification service | Register devices, send push via Notification Hubs and email via Azure Communication Services for new/reopened cases, assignments, overdue follow-ups and checks due. | • Users receive only notifications for their role/scope • Notification opens the right record (deep link) |  | Must | 3 | INF-009, BE-017 | POC core | Not started
BE-023 | 3. Build | M10 Audit & Traceability | Backend | Audit query and export API | Search audit events by animal, case, user, date/time and action. Export to CSV. | • Only auditors/admins can query • Export itself is audited |  | Must | 2 | BE-006 | POC core | Not started
BE-024 | 3. Build | M2 Animal Profile & Health Record | Backend | Reports and exports | Export an animal health record for a stay and a case report as PDF, and case lists as CSV. | • PDF includes summary, timeline and evidence thumbnails • Exports respect user scope |  | Should | 3 | BE-020 | POC core | Not started
BE-025 | 3. Build | M12 Notifications | Backend | Scheduled jobs | Checks-due reminders per AM/PM session, overdue follow-up escalation to supervisors, and retention/archiving jobs. | • Jobs are idempotent and logged • Escalation fires after the configured overdue period |  | Should | 2 | BE-022 | POC core | Not started
BE-026 | 3. Build | Platform / Cross-cutting | Backend | Backend automated tests | Unit tests for services and rules, integration tests against a real PostgreSQL, contract tests against the OpenAPI spec. | • 70%+ line coverage on services • Tests run in the pipeline |  | Must | 5 | BE-018 | POC core | Not started
AI-001 | 3. Build | M6 AI Routing & Extraction | AI | AI gateway module | Shared client for Azure OpenAI with retries, timeouts, prompt versioning, structured-output validation, token usage tracking and logging of inputs/outputs for audit. | • Every call logs prompt version, model, latency and tokens • Timeouts fall back without losing the observation |  | Must | 3 | INF-008 | POC core | Not started
AI-002 | 3. Build | M6 AI Routing & Extraction | AI | Animal matching | Find candidate animals from kennel code and name (fuzzy match, active stays only), then ask the model to pick one using recent history. Return a confidence score. | • Top-1 match accuracy ≥ 95% on the evaluation set • No match returned for released animals | 06 | Must | 4 | AI-001, REQ-008 | POC core | Not started
AI-003 | 3. Build | M6 AI Routing & Extraction | AI | Clinical sign extraction | Extract signs (standard taxonomy), body system, onset date, severity cues and consumption/stool/urine values from free text and inspection data. Inject the AQC glossary. | • Output always validates against the JSON schema • Sign-level F1 ≥ 0.85 on the evaluation set | 06 | Must | 4 | AI-001, REQ-004 | POC core | Not started
AI-004 | 3. Build | M6 AI Routing & Extraction | AI | Routing suggestion | Compare extracted signs with the animal's open and recently closed cases and suggest: timeline only, update case, new case or reopen, with a short rationale. | • Suggested action matches the labelled action ≥ 85% • Rationale cites the case it refers to | 06 | Must | 3 | AI-003, BE-018 | POC core | Not started
AI-005 | 3. Build | M7 AI Clinical Summary | AI | 30-day clinical summary | Generate a date-aware summary per animal from its own records (e.g. 'GI upset since 21/08, 4 observations in 7 days'). Each statement cites source record IDs. Regenerate on new data. | • Every statement has at least one valid citation • Summary refreshed within 1 minute of a new record | 08 | Must | 4 | AI-001, BE-020 | POC core | Not started
AI-006 | 3. Build | M6 AI Routing & Extraction | AI | AI worker orchestration | Consume events from Service Bus and run match → extract → route. Save the AI result for the confirmation screen. Send failures to the review queue. | • Dead-letter handling with alert • End-to-end result in under 15 seconds (p90) | 06 | Must | 3 | AI-002, AI-003, AI-004, BE-016 | POC core | Not started
AI-007 | 3. Build | M6 AI Routing & Extraction | AI | AI guardrails | Reject outputs with invalid schema or citations to records that don't exist. Handle content-filter blocks. Strip personal data from logs. | • Invalid outputs never reach users • Guardrail hits counted in monitoring |  | Must | 2 | AI-006 | POC core | Not started
AI-008 | 3. Build | M6 AI Routing & Extraction | AI | Evaluation harness and threshold tuning | Script that runs the evaluation set through the pipeline and reports match, extraction and routing accuracy. Use it to set confidence thresholds. | • Report generated per prompt version • Thresholds documented and configurable |  | Must | 4 | AI-006, REQ-008 | POC core | Not started
FE-001 | 3. Build | Platform / Cross-cutting | Frontend | App scaffold (Expo + React Native Web) | Expo app with TypeScript, Expo Router navigation, TanStack Query for server state, a typed API client generated from OpenAPI, and environment config. Runs on iOS, Android and web. | • Same codebase runs on iOS, Android and browser • API client regenerates from the spec |  | Must | 3 | INF-001, DES-006 | POC core | Not started
FE-002 | 3. Build | Platform / Cross-cutting | Frontend | Component library | Build the design-system components: buttons, cards, status chips, form fields, normal/abnormal toggles, segmented choices (e.g. mentation), bottom sheets, toasts, list rows. | • Components themed from design tokens • Storybook (or equivalent) page for each component |  | Must | 4 | FE-001, DES-003 | POC core | Not started
FE-003 | 3. Build | Platform / Cross-cutting | Frontend | Login and session management | OIDC Authorization Code + PKCE (expo-auth-session) with a choice of officer or contractor login. Tokens in SecureStore, silent refresh, logout, and biometric unlock on reopen. | • Both user types can sign in with MFA • Session expires after the agreed idle time |  | Must | 4 | FE-001, INF-007 | POC core | Not started
FE-004 | 3. Build | Platform / Cross-cutting | Frontend | Role-based navigation | Show screens and actions based on role (e.g. contractors don't see New Arrival or Close case). | • Hidden actions are also blocked by the API • Bottom tabs: Operations, Daily Inspection, Medication, Cases | 01 | Must | 1 | FE-003 | POC core | Not started
FE-005 | 3. Build | M9 Operations Dashboard | Frontend | Operations home screen | Quick actions (New Arrival, New Health Observation), today's monitoring counts (active pets, checks due, open cases) and alert cards (e.g. 'KC2-2 Yang Yang · GI observation requires review'). | • Counts refresh on pull-to-refresh and on return to screen • Tapping an alert opens the case | 01 | Must | 3 | FE-002, BE-021 | POC core | Not started
FE-006 | 3. Build | M2 Animal Profile & Health Record | Frontend | Animal picker and search | Pick an animal by kennel code, name or microchip, with recent animals first. Used by inspections, observations and medication. | • Search returns results as you type • Contractors only see their kennels | 04, 05, 07 | Must | 2 | FE-002, BE-009 | POC core | Not started
FE-007 | 3. Build | M1 Arrival & Onboarding | Frontend | New Arrival screen (step 1 of 2) | Form for pet name, kennel/room, species, country of origin, microchip no., sex, date of birth and release date, then continue to the arrival exam. | • Field validation matches the data dictionary • Draft kept if the user leaves the screen | 02 | Must | 3 | FE-002, BE-009 | POC core | Not started
FE-008 | 3. Build | M1 Arrival & Onboarding | Frontend | Arrival Exam screen (step 2 of 2) | Examining vet, weight, mentation choice (Responsive/Calm/Active/Alert), and physical exam rows (skin/coat, eyes, nose, ears, mouth, hydration, respiratory) as Normal/Abnormal with notes and photos. | • Abnormal rows require a note • Completing the exam opens the Animal Profile | 03 | Must | 3 | FE-007, BE-010 | POC core | Not started
FE-009 | 3. Build | M3 Daily Health Inspection | Frontend | Daily Inspection screen (AM/PM) | Checklist for mentation, body systems, food (e.g. Full), stool (e.g. Firm), urine (Yes/No) and other findings. All default to Normal so a healthy animal takes a few taps. | • Healthy-animal inspection submits in under 30 seconds • Next due animal offered after submit | 04 | Must | 4 | FE-006, BE-011 | POC core | Not started
FE-010 | 3. Build | M4 Ad-hoc Health Observation | Frontend | New Health Observation screen | Pick the animal, add photos/videos (camera or gallery), describe what was seen, and submit for AI assistance. | • Photos compressed on device before upload • Submission works with the text alone | 05 | Must | 4 | FE-006, FE-011, BE-012 | POC core | Not started
FE-011 | 3. Build | M4 Ad-hoc Health Observation | Frontend | Media upload manager | Upload media with SAS URLs in the background, show progress, retry on failure, and resume after the app is reopened. | • Upload survives app backgrounding • Failed uploads are visible and can be retried | 05 | Must | 3 | FE-001, BE-013 | POC core | Not started
FE-012 | 3. Build | M6 AI Routing & Extraction | Frontend | AI Confirmation screen | Show the matched pet record, extracted signs, evidence linked and the routing suggestion ('add to 30-day timeline and update/create case'), with confidence. Actions: Correct, Confirm & Route. | • User can change the animal, signs or action before confirming • Low confidence clearly flagged as 'Review required' | 06 | Must | 3 | FE-010, AI-006 | POC core | Not started
FE-013 | 3. Build | M5 Medication Administration | Frontend | Medication Administration screen | Show medication/supplements due for the selected pet (e.g. Probiotic 5 mL 2x daily), record as administered with remarks. Time and officer captured automatically. | • Due and overdue doses visible • Double-recording the same dose is prevented | 07 | Must | 3 | FE-006, BE-015 | POC core | Not started
FE-014 | 3. Build | M2 Animal Profile & Health Record | Frontend | Animal Profile screen | Header (name, kennel, species, monitoring status), today's status (arrival, AM/PM inspection), quick actions, AI 30-day summary card with evidence links, and the longitudinal health record timeline. | • Tapping a summary citation opens the source record • Timeline filters by record type | 08 | Must | 4 | FE-002, BE-020, AI-005 | POC core | Not started
FE-015 | 3. Build | M8 Health Case Management | Frontend | Health Cases list | Officer workbench list: animal, finding, status chip (Open/Review/Closed) and filters. | • Filters: open, needs review, last 7 days, assigned to me • List updates after status changes | 09 | Must | 3 | FE-002, BE-017 | POC core | Not started
FE-016 | 3. Build | M8 Health Case Management | Frontend | Case detail | Case summary, linked observations timeline, evidence gallery, assignment, follow-up actions, notes, close (with reason) and manual reopen. | • Close requires a reason • Reopened cases show the full earlier history | 09 | Must | 4 | FE-015, BE-018 | POC core | Not started
FE-017 | 3. Build | M6 AI Routing & Extraction | Frontend | Review queue screen | Officer triage for unmatched or low-confidence observations: pick the animal and case action manually. | • Queue count shown on Operations home • Triaged items disappear from the queue |  | Must | 2 | FE-012, BE-019 | POC core | Not started
FE-018 | 3. Build | M4 Ad-hoc Health Observation | Frontend | Offline capture | Save inspections, observations and medication records locally (SQLite) when offline and sync in order when back online. Show pending items. | • Records made offline sync without duplicates • User sees which items are still pending | 04, 05, 07 | Should | 5 | FE-009, FE-010, FE-013 | POC core | Not started
FE-019 | 3. Build | M12 Notifications | Frontend | Push notifications | Register the device, request permission, handle notifications in foreground/background and deep-link to the case or animal. | • Tapping a notification opens the right screen • Device unregistered on logout |  | Must | 2 | FE-003, BE-022 | POC core | Not started
FE-020 | 3. Build | M9 Operations Dashboard | Frontend | Web workbench shell | Responsive desktop layout for the browser build: sidebar navigation, top bar, wide data tables and split views. | • Usable at 1440px and 768px • Mobile layout unchanged |  | Must | 4 | FE-002 | POC core | Not started
FE-021 | 3. Build | M9 Operations Dashboard | Frontend | Web operations dashboard | Table of unwell animals (animal, status, AI summary, action) with filters and quick assign, plus today's counts. | • Sort and filter without page reload • Assign follow-up from the table | 09 | Must | 3 | FE-020, BE-021 | POC core | Not started
FE-022 | 3. Build | M10 Audit & Traceability | Frontend | Audit view (web) | Search audit events by animal, case, user, date/time and action; view before/after; export CSV. | • Visible to auditors and admins only • Export downloads CSV |  | Must | 2 | FE-020, BE-023 | POC core | Not started
FE-023 | 3. Build | M11 Administration | Frontend | Admin screens (web) | Manage users/roles and kennel scopes, kennels/rooms, species, checklist templates, symptom taxonomy, AQC glossary and notification rules. | • All master data editable without a deployment • Changes audited |  | Must | 5 | FE-020, BE-007, BE-008 | POC core | Not started
FE-024 | 3. Build | M4 Ad-hoc Health Observation | Frontend | Evidence viewer | Full-screen image viewer with zoom and a video player for evidence on mobile and web. | • Media loads via short-lived read URLs • Nothing saved to the device photo gallery | 08, 09 | Must | 2 | FE-011 | POC core | Not started
FE-025 | 3. Build | Platform / Cross-cutting | Frontend | States and accessibility | Loading, empty, error and offline states on every screen. Accessibility labels, contrast and dynamic font size support. | • All screens pass the accessibility checklist • Web meets WCAG 2.1 AA on key pages |  | Should | 3 | FE-016 | POC core | Not started
FE-026 | 3. Build | Platform / Cross-cutting | Frontend | Mobile app security | Root/jailbreak detection, certificate pinning, screenshot protection on sensitive screens, clearing cached data on logout. | • Checks pass OWASP MASVS L1 items in scope • Cached data removed on logout |  | Should | 2 | FE-003 | Production hardening | Not started
FE-027 | 3. Build | Platform / Cross-cutting | Frontend | Frontend automated tests | Component tests (Jest + React Native Testing Library), mobile E2E (Maestro) for the main flows, and web E2E (Playwright). | • E2E covers arrival, inspection, observation → AI confirm → case close • Tests run in the pipeline |  | Must | 5 | FE-016 | POC core | Not started
[8 empty] | Total | 193 | ← sums only visible (filtered) rows